## Timeline of Tasks
NCAPER 3-YEAR Implementation Planning Worksheet Timeline - created in February 2019; updated October 2019
TASKS | RESPONSIBILITIES | Mellon Year 1 - 2018 |  | Mellon Year 2 - 2019 |  | Mellon Year 3 - 2020 |  | OUTCOMES
|  | Jan-June | July- Dec. | Jan-June | July- Dec. | Jan-June | July- Dec.
INFRASTRUCTURE
Recruit & hire Executive Director | Co-chairs; Steering Committee | P | [5 empty] | Jan Newcomb hired 2/15/18
Setup NCAPER Admin with fiscal agent | South Arts - fiscal agent |  |  | P |  |  |  | Agreement created and signed by South Arts & NCAPER
Recuit & Hire Program Associate | ED & Co-chairs | P | P |  |  |  |  | Jordan Young hired in Feb.; Lynn Dates hired in mid August to replace him
Orient and supervise ED | South Arts, Co-chairs | P | P | P | P | P | P | Orientation to SouthArts ways is ongoing; bi-monthly calls with co-chairs has now changed to monthly calls.
Setup regular NCAPER meetings | ED & Co-chairs | P | P | P | P | P | P | Schedule of meetings is published each January at the onsite meeting; have now changed to quarterly meetings for the rest of 2019 and 2020.
Implement the Proposed membership structure to create a national communications network for building resilience within the entire arts sector and to build a reliable, renewable revnue stream for NCAPER | ED, Membership Working group; Steering Committee and selected outside colleagues |  |  |  |  | P | P | Still in progress: Develop annual goals for $ and # of members. Promote membership by PAR network grantees to develop interaction among them. The idea of NCAPER membership is to broaden the base of organizations that serve the field and artists who can disseminate information to their stakeholders
Introduced to funders | ED, SouthArts |  | P |  |  |  |  | Traveled to NYC with S. Surkamer to meet with staff @ Mellon Fndn, GIA, Tremaine Fndn, GIA, Joan Mitchell Fndn, Creative Capital & NCAPER Steering Committee members
PROGRAMMATIC AGENDA
Design, register, and publish ncaper.org | ED, Program Associate; marketing/communications work group |  | P |  |  |  |  | Logo designed by J. Young in July; ncaper.org designed, licensed & published by L. Dates in October
Participate and attend onferences, focus groups and workshops supported by PAR | ED, Co-chairs; PAR Director | P | P | P | P | P | P | Participated in 14 conferences January-December 2018; so far in 2019, participated in 12 conferences; developed 2 additional conference sessions for GIA and Artists in Communities conferences
Begin contact with national partners (arts & non-arts) | ED |  | P | P | P | P | P | Maine International Conference in Sept.; VA Commission on the Arts - 1/30/19; Delaware Arts Summit in Oct. 2019; in addition to the CAC partnership, MQH and JN has begun discussions with SMU Data Arts.
Develop relationships with federal, state, local arts and cultural partners to pormote visibility and attend 4-5 conferences/yr. not covered by PAR to promote NCAPER and PlaceKeeping Guide, Studio Protector, etc. | ED; steering committee members, outside colleagues |  |  | P | P | P | P | Joined HENTF; participate on HENTF disaster response calls with FEMA and federal culture agencies. Have volunteered to work with Lori Foley in developing ways to collect data on assessing loss for artists and arts organizations following disasters.
Advocate for the arts sector as an essential collaborator in broader societal efforts for preparedness, emergency response and recovery by attending convenings and building relationships. | ED; steering committee members, NEA |  |  |  |  | P | P | Connecting cultural networks that are created by PAR grants began in April during discussions with the California Arts Council. Since then PAR & NCAPER developed a webinar and nine 5-hour training sessions which were given in August & September.
Develop the ONLINE TOOL implementation strategies for maintaining it on NCAPER.org | ED, Program Associate, MQH, F. Harrell, NEDCC |  |  |  |  | P | P | Despite weekly calls, the work progress is slow and the launch has been delayed because of legal discussions earlier this year.
Develop a CREATE Act Education campaign as an advocacy tool to support artists and arts organizations after disasters. | ED; steering committee members, outside colleagues |  |  |  |  | P | P | Design a programmatic plan to increase cross-sector understanding of CREATE Act legislation loopholes. No work on this has been discussed or developed.
Review and update Response Protocol
Assemble an Ad Hoc committee of local leaders from recent crises to advise and refine NCAPER's response protocol for future crises based on lessons learned. Build on NCAPER Disaster Communications Protocol (2/2016) & Essential Guidelines for Arts Responders Organizing in the Aftermath of Disaster | ED, Co-chairs; Marketing Communications working group |  |  |  |  | P | P
Respond to disasters | on an as needed basis throughout the 3 years
Disaster phone call coordination | ED, Steering Committee | P | P | P | P | P | P | YR 1: Hosted 60 phone calls with nearly 1,000 people
On-site response | ED |  | P | P | P | P | P | Traveled to Trenton, NJ to meet with board & management of ArtWorks
Interviews | ED |  | P | P | P | P | P | Published interview with C. Stinson of Arts Friendly - RE: NC response to Hurricane Michael
Other - including the idea of hosting or sharing the hosting of a convening |  | P | P | P | P | P | P | Hired Amy Schwartzman to prepare a bi-lingual flyer focusing on the needs of performing and literary artists before, during and after crises. This was done in conjunction with CERF+ in response to needs of artists in PR and USVI
Develop Response Team capability
Develop a response approach to deploy experts who can aid artists and arts organizations immediately after a disaster. Develop a Response Team roster of specialists with expertise in the following areas: 1. Assessment - to collect and identify needs and assessments of individual artists, venues, organizations, etc. 2. Aid - to provide direction on existing fundraising or grantmaking efforst and matching in-kind services and goods. 3. Sustainability - to develop long-term strategies that serve as guides for mitigating the overarching concerns that impact viable sustainability. | [5 empty] | P | P
Research how to develop an NCAPER Help Desk responding to needs of artists and arts organizations before, during and after crises. | [5 empty] | P | P | A 1-800 toll free number will be acquired and a process developed for responding to calls using FAIC as an example. Help Desk contractors @ $1,500/week, average 2 contractors for 2 weeks per disaster.
Supervise and manage assignments and deployments | [5 empty] | P | P
Create Studio Protector for Performing Artists
Contract for the adaptation of the existing Studio Protector which is designed for individual visual and craft artists. Address the gaps in the existing Studio Protector in order to be responsive to performing artists | [5 empty] | P |  | Hire a contractor to create the adaptation and design for online performing artist version.
MARKETING/PROMOTION/COMMUNICATIONS
Continue to build an online visual identify for NCAPER that incorporates the online tool. Plan with PAR and ArtsReady to develop strategies to house resources and information (post grants) | ED, Program Associate, MQH, F. Harrell, NEDCC, Tom Clareson |  | P | P | P | P | P
Develop scope of work/story boards for videos; hire videographer and arrange interviews |  |  | P | P | P | P | P | Hired Laura Ashermann of Forage Films, Atlanta to implement the scope of work; she interviewed during GIA and the January 3, 2019 Steering Committee meeting in NYC
Update and promote publications | ED, Marketing/Communications work group, steering committee |  | P | P | P | P | P
Develop a Marketing/Communications plan including videogrpahy to promote an online presence of NCAPER (web & social media) & at conference sessions | ED, Program Associate, Marketing/Communications Work group |  | P | P | P | P | P
Develop webinars specifically targeting issues of artist groups, arts organizations | ED, Tom Clareson, PAR, Barbara Davis, The Actors Fund |  |  | P | P | P | P
Develop an inventory of low-cost, high-touch tools to enhance the ability of disaster-impacted people to absorb and apply information and actions. |  |  |  |  | P | P |  | Create short videos describing emotional and chronological arc of a disaster on artists and artsworkers - what emergency response triggers happen in the first day(s) and the first month (depending on severity) following a disaster, and when and how arts responders should take action and guidance on helping ot match up ai that's needed with aid that is offered

## Budget FY Actuals & Projections
NCAPER 3-YEAR Implementation Planning Worksheet Budget
[6 empty] | Mellon Year One |  | Mellon Year Two |  | Mellon Year Three
[7 empty] | South Arts FY19 |  | South Arts FY20 |  | South Arts FY21
|  |  | Other | Mellon | Account # | Jan-June 18 Actual | July- Dec. 18 Actual | Jan-June19 Projected | July-Dec19 Projected | Jan-June20 Budgeted | July-Dec20 Budgeted | Jan-April 21
Deliverable Category | Task | Description of expense | 01 | 02
Infrastructure | Fiscal agent supervision | SouthArts - MQH salary & payroll costs | P |  | 5000, 5010, 5020, 5030 |  | 3805.08 | 3805.08
| Hire ED | Jan salary & payroll taxes |  | P | 5000, 5010 | 22207 | 26760 | 27600 | 27429 | 28114.725 | 28114.725
| Hire Program Associate | Jordan & Lynn | P | P | 5000, 5276 | 2821 | 3145 | 7200 | 7200 | 7380 | 7380
| Design logo & launch website |  |  | P | 5250 | 115
| License & Taxes | ncaper.org one-year license |  | P | 5230 |  | 300
| Telecommunications | Video conferencing fee |  | P | 5320 |  | 149.9 | 0
| Dues | APAP membership; website hosting |  | P |  |  | 1214 | 2000
| Printing | Bi-fold for PR purposes |  | P | 5265 |  | 622.48 | 628
| Supplies | computer supplies |  | P | 5310,5305 | 249 | 271.88 | 978
| Rent | Overhead charge for NCAPER |  | P | 5240 | 1832 | 2849.28 | 2177.5 | 2177.5 | 2232.5 | 2232.5
| Postage & Courier |  |  | P | 5260 | 30
| Travel: director |  |  | P | 5100 | 1222 | 1787.09 | 7300 | 7300
| Shipping Crating/Storing |  |  | P | 5485 |  |  | 500
Program Agenda | Program development | Consultants |  | P | 5420 | 6450
| Placekeeping/Network review & Update | Consultant - coordinate PAR networks & revise/update Placekeeping Guide |  | P | 5420, |  |  | 7500
| Conference participation | travel of participants including co-chairs |  | P | 5140 | 206 |  | 3000 | 6000
| GIA | travel of speakers |  | P | 5130 |  | 4113.74 | 5000
|  | travel of staff |  | P | 5100 |  | 2521.87 | 4000 | 3000
| Response Team Efforts | USVI AR & bi-lingual sheet dev. |  | P | 5276,5285 |  | 3595 |  | 9000
| National Convening Planning |  |  | P | 5420 |  |  | 1500
| SWAT Team Development/Training | Consultant |  | P |  |  |  | 10000 | 10000
| Equipment Rental | at conferences/presentations |  | P | 5430 |  |  | 500
| Exhibition supplies |  |  | P | 5440 |  |  | 500
Marketing | Video shoot for website & online tool |  |  | P | 5400 |  | 8926 | 10000
| Membership campaign | Cost of additional module for website - Paypal or other payment. Design & print "handout"; extra postage, etc. |  | P | 5265, 5260 |  |  | 5000 | 5000
| Exhibition SAF |  | P |  | 5435 | 0 | 150
| Banner advertising |  |  | P | 5400 |  | 0 | 3500 | 1750 | 1750 | 1750
TOTAL EXPENSE | [5 empty] | 35132 | 60211.32 | 102688.58 | 78856.5
[6 empty] | Mellon Year One |  | Mellon Year Two |  | Mellon Year Three
[6 empty] | BUDGETED | ACTUAL | BUDGETED | Projected | BUDGETED | Projected
[6 empty] | 192070 | 95343.32 | 152975 | 181545.08
Note on H7: Lynn Rhoda Dates: Mollie #5000 2996.10 #5010 344.58 #5020 284.64 #5030 179.76
Note on I7: Lynn Rhoda Dates: Mollie #5000 2996.10 #5010 344.58 #5020 284.64 #5030 179.76
Note on H8: Janet Newcomb: 24,000 salary 5000 2760 payroll taxes 5010
Note on I13: Janet Newcomb: Join AFTA, NVOAD,